## Guide
GT AI Strategy & Roadmap Toolkit
Companion to 'GT Bahrain AI Strategy & Roadmap 2026-2028'. Populated with the GT Bahrain case; reusable as a template for client AI strategy engagements.
| 1. SWOT & TOWS | Situational analysis: strengths, weaknesses, opportunities, threats and the resulting strategic options (TOWS).
| 2. Use-Case Scoring | Score candidate use cases 1-5 on four value and four feasibility criteria (weights editable in row 5). Value, feasibility, quadrant and priority rank calculate automatically.
| 3. Roadmap (Gantt) | Enter start month (1 = Oct 2026) and duration for each activity; the Gantt bars draw automatically. Track owner and status.
| 4. KPI Tracker | Baseline, targets and actuals for strategy KPIs; RAG status calculates from the actual value where numeric.
| 5. Ready7 Traceability | Maps every AI Ready7 item not fully met to a roadmap response, horizon and workstream.
| Colour legend | Yellow = input ¦ Purple = header / calculated

## 1. SWOT & TOWS
1. SWOT & TOWS Analysis
Internal factors from the AI Ready7 baseline (Sept 2026); external factors from the Bahrain / GCC landscape scan.
| STRENGTHS | WEAKNESSES
| Strong global brand and GTIL network; AI Ready7 methodology already in use | Overall AI readiness 'Informed' (61.4%) - below the 'Repeatable' threshold
| Deep audit, GRC, cyber and regulatory heritage - a credible trust-first position | No consistent lifecycle AI risk assessment (Ready7 2.4 - Not Met)
| Existing relationships in regulated sectors (banking, telecom, government) | Data classification & handling for AI not in place (Ready7 5.1 - Not Met)
| Compliance & data foundations in place (Ready7 2.2, 2.5, 5.3, 5.4 fully met) | Business alignment 50%: strategy, portfolio and value tracking only partially defined
| Good AI literacy (T&D 69%) and threat defence (70%) baseline | Architecture & AI security at 55%: reference architecture, red teaming, ModelOps immature
| Four defined AI service lines and proprietary tools (RCM v2.0, risk framework, readiness tool) | Limited in-house AI engineering capacity; reliance on vendor tools
| OPPORTUNITIES | THREATS
| National AI agenda: Vision 2030, iGA AI Policy (2025), UNESCO AI readiness report (2025) | Big Four and tech-native AI consultancies competing aggressively (e.g., EY.ai, niche AI firms)
| Regulation wave: PDPL, CBB, GCC regimes, EU AI Act reach, forthcoming Bahrain AI law | Fast-moving technology and vendor lock-in risk
| Emerging ISO/IEC 42001 certification and AI assurance market in the GCC | AI-enabled cyber threats and deepfake fraud targeting the firm and its clients
| Sector demand in financial services, insurance, government, telecom, healthcare, hospitality | Client-confidentiality and professional-liability exposure from AI errors
| AI productivity gains in audit, tax and advisory delivery improve margins and quality | Scarcity of AI talent across the GCC
| Regional scale through the GT network across the GCC | Regulatory uncertainty (Bahrain AI law timing, EU Digital Omnibus changes)
TOWS - STRATEGIC OPTIONS
| SO - Lead with trust | Launch governance-led AI offerings (readiness assessment, AI GRC / RCM review, ISO/IEC 42001 readiness) into regulated sectors, leveraging the GT brand and GRC heritage.
| WO - Become 'client zero' | Close our own gaps (risk assessment, data classification, strategy & portfolio) using our own tools - and turn the journey into a reference case.
| ST - Differentiate on assurance + security | Combine AI GRC with cyber (AI red teaming, deepfake resilience) to stand apart from technology-led competitors.
| WT - Partner and protect | Vendor-agnostic alliances, strict client-data guardrails and targeted hiring / upskilling to contain talent, liability and lock-in risks.

## 2. Use-Case Scoring
2. Use-Case Prioritisation
Score 1 (low) - 5 (high). Technical simplicity and ease of change: 5 = easiest. Weights (row 5) must total 100% per dimension. Quadrant threshold (cell B3) editable.
Quadrant threshold | 3.5
# | Use case | Area | Risk tier | Strategic alignment | Efficiency / financial benefit | Quality & client impact | Scalability / reuse | Data readiness | Technical simplicity | Ease of change & adoption | Tool / vendor availability | VALUE | FEASIBILITY | Quadrant | Priority rank | Horizon
| Weights |  |  | 25% | 35% | 25% | 15% | 30% | 25% | 20% | 25%
1 | Proposal & report drafting assistant | All service lines | Medium | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 5 |  |  |  |  | H1
2 | Meeting transcription & summaries | Firm-wide | Low | 3 | 3 | 3 | 4 | 5 | 5 | 4 | 5 |  |  |  |  | H1
3 | Knowledge assistant (methodology RAG) | Firm-wide | Medium | 5 | 4 | 4 | 4 | 3 | 4 | 4 | 4 |  |  |  |  | H1
4 | Audit analytics & anomaly detection | Audit & Assurance | High | 5 | 5 | 5 | 4 | 3 | 2 | 3 | 4 |  |  |  |  | H2
5 | Tax research & regulatory Q&A | Tax | Medium | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 |  |  |  |  | H2
6 | Contract & document review | Advisory / Due diligence | Medium | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 4 |  |  |  |  | H2
7 | Client onboarding / KYC screening | Risk & Quality | High | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | H3
8 | AI-assisted control testing (RCM) | Risk Advisory / AI GRC | Medium | 5 | 4 | 3 | 4 | 3 | 3 | 4 | 4 |  |  |  |  | H2
9 | Finance, timesheet & billing automation | Operations | Low | 2 | 4 | 2 | 3 | 4 | 4 | 3 | 5 |  |  |  |  | H2
10 | Marketing & thought-leadership content | Marketing | Low | 2 | 2 | 3 | 3 | 5 | 5 | 5 | 4 |  |  |  |  | H1
11 | Agentic engagement workflow assistant | Firm-wide | High | 5 | 5 | 4 | 4 | 2 | 1 | 2 | 3 |  |  |  |  | H3
12 | Client AI readiness self-assessment portal | AI service line | Medium | 5 | 4 | 4 | 5 | 3 | 3 | 4 | 3 |  |  |  |  | H2

## 3. Roadmap (Gantt)
3. Implementation Roadmap - Oct 2026 to Mar 2028
Start month: 1 = Oct 2026. Bars draw automatically from Start and Duration. Dashed milestones: H2 starts Apr 2027 (month 7), H3 starts Jan 2028 (month 16).
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Workstream | Activity | Start | Duration | End | Owner | Status | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27 | Nov-27 | Dec-27 | Jan-28 | Feb-28 | Mar-28
WS1 Governance & Risk | AI strategy, risk appetite & acceptable-use policy | 1 | 2 |  | Risk & Quality / AI CoE | Not started
WS1 Governance & Risk | AI Steering Committee & CoE charter | 1 | 2 |  | Risk & Quality / AI CoE | Not started
WS1 Governance & Risk | AI register refresh & risk-framework rollout | 2 | 4 |  | Risk & Quality / AI CoE | Not started
WS1 Governance & Risk | Vendor AI contract clauses & due diligence | 3 | 4 |  | Risk & Quality / AI CoE | Not started
WS1 Governance & Risk | ISO/IEC 42001 gap assessment & AIMS build | 6 | 8 |  | Risk & Quality / AI CoE | Not started
WS1 Governance & Risk | Certification-readiness audit | 14 | 3 |  | Risk & Quality / AI CoE | Not started
WS2 People & Skills | AI literacy baseline (all staff) | 2 | 5 |  | HR / L&D | Not started
WS2 People & Skills | Role-based pathways & AI champions network | 5 | 7 |  | HR / L&D | Not started
WS2 People & Skills | Leadership & client-facing enablement | 7 | 6 |  | HR / L&D | Not started
WS2 People & Skills | Annual refresh & workforce plan | 13 | 6 |  | HR / L&D | Not started
WS3 Data, Platforms & Security | Data classification for AI & GenAI DLP | 1 | 4 |  | IT / Cyber | Not started
WS3 Data, Platforms & Security | Enterprise GenAI platform & reference architecture | 2 | 6 |  | IT / Cyber | Not started
WS3 Data, Platforms & Security | AI red teaming & deepfake-resilient processes | 4 | 6 |  | IT / Cyber | Not started
WS3 Data, Platforms & Security | Monitoring, KRIs, logging & ModelOps | 7 | 7 |  | IT / Cyber | Not started
WS4 Use Cases & Value | Quick wins: drafting, transcription, knowledge assistant | 2 | 5 |  | AI CoE + service lines | Not started
WS4 Use Cases & Value | Pilots: audit analytics, tax assistant, document review | 6 | 6 |  | AI CoE + service lines | Not started
WS4 Use Cases & Value | Scale proven use cases; agentic pilots | 12 | 7 |  | AI CoE + service lines | Not started
WS5 AI Service Line (GTM) | Package offerings & tools; pricing approach | 1 | 3 |  | AI service line lead | Not started
WS5 AI Service Line (GTM) | Launch & first pilot clients | 4 | 4 |  | AI service line lead | Not started
WS5 AI Service Line (GTM) | Sector campaigns (FS, government, telecom) | 7 | 7 |  | AI service line lead | Not started
WS5 AI Service Line (GTM) | Regional scale via the GT network | 13 | 6 |  | AI service line lead | Not started

## 4. KPI Tracker
4. KPI Tracker
Update 'Actual' each quarter. Status is set manually (On track / At risk / Off track) based on trajectory to target.
KPI | Baseline (Sept 2026) | Target end-2027 | Target end-2028 | Owner | Actual (latest) | Status | Commentary
AI Ready7 overall readiness | 61.4% (Informed) | >= 75% (Repeatable) | >= 85% | AI CoE lead
Governance & Ethics pillar | 60% | >= 80% | >= 90% | Risk & Quality partner
AI use cases risk-tiered & assessed (AI register) | Register exists; assessment not consistent | 100% by Q1 2027 | 100% + quarterly reconciliation | AI CoE
Staff completing AI literacy | To be baselined | >= 90% by Q2 2027 | 100% (annual refresh) | HR / L&D
Production AI use cases with measured benefits | 0 measured | 6 | 10+ | Service-line leaders
Time saved in targeted processes | To be baselined | 10% | 15% | CoE + Finance
AI advisory engagements delivered (proposed) | Pilot stage | 12 | 25 | AI service line lead
Client-data leakage incidents via AI | - | 0 | 0 | CISO / DPO
ISO/IEC 42001 status | Not started | Certification-ready | Certified (optional) | Risk & Quality partner

## 5. Ready7 Traceability
5. AI Ready7 Gap-to-Roadmap Traceability
AI Ready7 self-assessment, GT Bahrain, 17 Sept 2026 - overall 61.4% (Informed). Pillar scores: Business Alignment 50%; Governance & Ethics 60%; Training & Development 68.75%; Architecture & Technology 55%; Data & Quality 70%; Protect AI Systems 55%; Protection from AI Threats 70%
Item | Title | Result | Roadmap response | Horizon | Workstream
1.1 | Strategy, Culture & Risk Appetite | Some Met | Approve AI strategy, executive sponsor and AI risk appetite | H1 | WS1
1.2 | Portfolio Governance | Some Met | Use-case intake, prioritisation and shadow-AI conversion | H1 | WS4
1.3 | Value Realisation | Some Met | Benefit KPIs and quarterly portfolio value reviews | H1-H2 | WS4
1.4 | Client & Stakeholder Assurance | Some Met | Publish responsible-AI statement for clients; ISO/IEC 42001 readiness | H2 | WS1
2.1 | AI Policy & Acceptable Use | Some Met | AI acceptable-use policy and approved-tools catalogue | H1 | WS1
2.3 | Adoption Guardrails & Ethical Standards | Some Met | AI CoE charter and practical guardrails | H1 | WS1
2.4 | Risk Assessment & Governance Reviews | Not Met | Roll out GT AI Risk Assessment Framework to all AI use cases & vendors | H1 | WS1
3.1-3.3 | Literacy, Validation, Security awareness | Most Met | Mandatory literacy refresh; deepfake simulations | H1-H2 | WS2
3.4 | Role-Based Capability Development | Some Met | Role-based pathways, AI champions, workforce plan | H2 | WS2
4.1 | Enterprise AI Reference Architecture | Some Met | Reference architecture v1 (data, models, agents, security) | H1-H2 | WS3
4.2 | Integration & Execution Authority | Some Met | Agent execution-authority standard and trust boundaries | H2 | WS3
4.3 | API, Access & Trust Enforcement | Some Met | Centralised API gateway / access control for AI | H2 | WS3
4.4 | Observability & Performance | Some Met | Monitoring with KRIs, thresholds and mandatory responses | H2 | WS3
4.5 | Cost, Compute & Platform Governance | Most Met | Governed pathway from citizen-developed AI to production | H2 | WS3
5.1 | Data Classification, Access & Handling | Not Met | Classification rules for AI, DLP on GenAI, data-readiness gate | H1 | WS3
5.2 / 5.5 | Human Oversight; Privacy safeguards | Most Met | Human-in-charge standard for deliverables; prompt redaction | H1 | WS1
6.1 | Identity, Access & Privilege | Most Met | Non-human / agent identity and credential management | H2 | WS3
6.2 | Data & Model Protection | Some Met | Vendor AI contract clauses (no training, residency, audit) | H1-H2 | WS1
6.3 | Secure AI Development & ModelOps | Some Met | Secure AI SDLC and ModelOps pipeline | H2 | WS3
6.4 | AI Security Testing | Some Met | AI red teaming of internal assistants before scale | H1-H2 | WS3
6.5 | Runtime Protection & Logging | Some Met | Runtime guardrails and forensic-ready AI logging | H2 | WS3
7.3 | Identity, Behavioural & Deepfake Defence | Some Met | Deepfake-resilient verification for payments & sensitive requests | H1-H2 | WS3
7.1/7.2/7.4/7.5 | Threat intel, SOC, IR, Exposure mgmt | Most Met | Sustain; add AI-specific scenarios to SOC and red teaming | H2-H3 | WS3